## Dashboard
Spark Lakehouse Lab - Progress Dashboard
Instacart ¦ PostgreSQL ¦ RustFS ¦ Apache Iceberg ¦ Spark 4.x standalone. All numbers on this sheet are formulas; do not type over them.
HOW TO USE
Yellow cells are yours to edit: Status (dropdown), Started, Completed and Evidence / notes on each checklist tab.
Status values: Not started, In progress, Blocked, Done, Skipped. Skipped items are excluded from % complete.
Example: set Status = Done, Completed = 2026-11-03, Evidence = 'E-014, D-003' (experiment and defect IDs).
Log every experiment on Experiments (prediction first), every data issue on Defects, every choice on Decisions.
Grey italic rows on the log tabs are examples: overwrite or delete them. Suggested order: Setup, P1 (M0-M5), P3 and P2, P1 (M2, M6-M8), P4, P5.
OVERALL PROGRESS
Scope | Detail | Total | Done | In progress | Blocked | Not started | Skipped | % complete | Next task
All areas | Setup + five projects | 498 | 0 | 0 | 0 | 498 | 0 | 0% | 0 of 498 items complete
BY AREA
Area | Open this tab | Total | Done | In progress | Blocked | Not started | Skipped | % complete | Next task (first In progress, else first Not started)
Setup and gates | Setup and gates (open tab) | 47 | 0 | 0 | 0 | 47 | 0 | 0% | Gate A: find the Iceberg Spark runtime artifact that matches your Spark minor version (Scala 2.13) on Maven Central. If the Spark 4.2 runtime is missing, pin Spark to the newest 4.x that has one. Record in Environment and Decisions.
Project 1 | Project 1: Lakehouse medallion ETL | 113 | 0 | 0 | 0 | 113 | 0 | 0% | Keep an untouched copy of the raw files in landing/raw_dump (everything must be reproducible from it).
Project 2 | Project 2: Joins, shuffles and skew | 91 | 0 | 0 | 0 | 91 | 0 | 0% | Freeze the data version: record Iceberg snapshot ids of lines, orders, products, aisles, departments, users, stores, price book, payments, events.
Project 3 | Project 3: Catalyst and query planning | 79 | 0 | 0 | 0 | 79 | 0 | 0% | Build lines/events variants: unsorted monthly-partitioned; sorted by product; z-ordered (department, hour); unpartitioned sorted; raw Parquet copy in landing.
Project 4 | Project 4: Executors, memory and I/O performance | 91 | 0 | 0 | 0 | 91 | 0 | 0% | Define W1-W6: scan-heavy, shuffle-heavy, CPU-heavy (per-line score), memory-heavy (cache + wide aggregation), write-heavy (layout rewrite), mixed user-feature build.
Project 5 | Project 5: Streaming and CDC into Iceberg | 77 | 0 | 0 | 0 | 77 | 0 | 0% | Clickstream producer around real baskets, with duplicates/replays, malformed lines, schema drift, out-of-order events and ~2% very late events.
SUPPORTING TRACKERS
Tracker | Measure | Count
Experiments | Logged | 0
Experiments | Prediction correct (Yes) | 0
Experiments | Prediction accuracy (Yes / answered) | 0%
Defects | On the register | 11
Defects | Handled | 0
Defects | Still to verify | 11
Decisions | Decided | 0
Decisions | Still open | 14
Config cards | Learned | 0
Config cards | Total | 33
BY MILESTONE
Area | Milestone | Total | Done | In progress | Blocked | Not started | Skipped | % complete
SU | S0 Gates and decisions | 5 | 0 | 0 | 0 | 5 | 0 | 0%
SU | S1 Platform bring-up | 10 | 0 | 0 | 0 | 10 | 0 | 0%
SU | S2 RustFS smoke tests | 8 | 0 | 0 | 0 | 8 | 0 | 0%
SU | S3 Dataset acquisition | 6 | 0 | 0 | 0 | 6 | 0 | 0%
SU | S4 Helpers | 12 | 0 | 0 | 0 | 12 | 0 | 0%
SU | S5 Conventions | 6 | 0 | 0 | 0 | 6 | 0 | 0%
P1 | M0 Load, profile, enrich | 19 | 0 | 0 | 0 | 19 | 0 | 0%
P1 | M1 Full extraction | 13 | 0 | 0 | 0 | 13 | 0 | 0%
P1 | M2 Incremental extraction | 11 | 0 | 0 | 0 | 11 | 0 | 0%
P1 | M3 Bronze | 12 | 0 | 0 | 0 | 12 | 0 | 0%
P1 | M4 Silver | 18 | 0 | 0 | 0 | 18 | 0 | 0%
P1 | M5 Gold | 13 | 0 | 0 | 0 | 13 | 0 | 0%
P1 | M6 Evolution and WAP | 7 | 0 | 0 | 0 | 7 | 0 | 0%
P1 | M7 Maintenance | 10 | 0 | 0 | 0 | 10 | 0 | 0%
P1 | M8 Orchestration and reconciliation | 10 | 0 | 0 | 0 | 10 | 0 | 0%
P2 | M0 Test bed and baselines | 6 | 0 | 0 | 0 | 6 | 0 | 0%
P2 | M1 Reading baseline plans | 6 | 0 | 0 | 0 | 6 | 0 | 0%
P2 | M2 Join strategies by hint | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P2 | M3 Federated joins | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P2 | M4 Diagnosing skew | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P2 | M5 Skew-fix ladder | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P2 | M6 Pair explosion | 10 | 0 | 0 | 0 | 10 | 0 | 0%
P2 | M7 Range joins | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P2 | M8 Partition sizing and writes | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P2 | M9 Storage-partitioned joins | 10 | 0 | 0 | 0 | 10 | 0 | 0%
P2 | M10 Memory pressure and spill | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P2 | M11 Anti-pattern gallery | 7 | 0 | 0 | 0 | 7 | 0 | 0%
P2 | M12 Synthesis | 2 | 0 | 0 | 0 | 2 | 0 | 0%
P3 | M0 Variants and query suite | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P3 | M1 Plan literacy | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P3 | M2 Iceberg pruning | 10 | 0 | 0 | 0 | 10 | 0 | 0%
P3 | M3 Runtime filtering | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P3 | M4 Statistics and cost-based planning | 7 | 0 | 0 | 0 | 7 | 0 | 0%
P3 | M5 JDBC pushdown | 13 | 0 | 0 | 0 | 13 | 0 | 0%
P3 | M6 AQE re-planning | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P3 | M7 Whole-stage codegen | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P3 | M8 Optimizer blockers | 12 | 0 | 0 | 0 | 12 | 0 | 0%
P3 | M9 Layout optimization | 7 | 0 | 0 | 0 | 7 | 0 | 0%
P3 | M10 Synthesis | 2 | 0 | 0 | 0 | 2 | 0 | 0%
P4 | M0 Workloads and baselines | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P4 | M1 Topology and strong scaling | 9 | 0 | 0 | 0 | 9 | 0 | 0%
P4 | M2 Memory model | 10 | 0 | 0 | 0 | 10 | 0 | 0%
P4 | M3 Serialization and RDD | 6 | 0 | 0 | 0 | 6 | 0 | 0%
P4 | M4 Python UDF ladder | 13 | 0 | 0 | 0 | 13 | 0 | 0%
P4 | M5 Object-store tuning | 12 | 0 | 0 | 0 | 12 | 0 | 0%
P4 | M6 JDBC concurrency | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P4 | M7 Concurrent writers | 9 | 0 | 0 | 0 | 9 | 0 | 0%
P4 | M8 Scheduling and allocation | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P4 | M9 Resilience | 7 | 0 | 0 | 0 | 7 | 0 | 0%
P4 | M10 Shuffle internals | 5 | 0 | 0 | 0 | 5 | 0 | 0%
P4 | M11 Capacity model | 2 | 0 | 0 | 0 | 2 | 0 | 0%
P5 | M0 Sources, speeds, SLOs | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P5 | M1 Clickstream to bronze | 9 | 0 | 0 | 0 | 9 | 0 | 0%
P5 | M2 Small files and maintenance | 6 | 0 | 0 | 0 | 6 | 0 | 0%
P5 | M3 Windowed aggregates | 7 | 0 | 0 | 0 | 7 | 0 | 0%
P5 | M4 Sessionization | 7 | 0 | 0 | 0 | 7 | 0 | 0%
P5 | M5 CDC apply | 11 | 0 | 0 | 0 | 11 | 0 | 0%
P5 | M6 Dedup and joins | 7 | 0 | 0 | 0 | 7 | 0 | 0%
P5 | M7 State and throughput tuning | 6 | 0 | 0 | 0 | 6 | 0 | 0%
P5 | M8 Failure drills | 8 | 0 | 0 | 0 | 8 | 0 | 0%
P5 | M9 Latency and SLOs | 6 | 0 | 0 | 0 | 6 | 0 | 0%
P5 | M10 Synthesis | 2 | 0 | 0 | 0 | 2 | 0 | 0%

## Setup
Setup and gates
Source: README sections 2-3 (bring-up and gates). Edit only the yellow cells: Status (dropdown), Started, Completed, Evidence / notes.
Progress | 0% | 0 of 47 items done ¦ In progress: 0 ¦ Blocked: 0 ¦ Skipped: 0
ID | Milestone | Task | Type | Status | Started | Completed | Evidence / notes
S0 Gates and decisions
SU-S0-01 | S0 Gates and decisions | Gate A: find the Iceberg Spark runtime artifact that matches your Spark minor version (Scala 2.13) on Maven Central. If the Spark 4.2 runtime is missing, pin Spark to the newest 4.x that has one. Record in Environment and Decisions. | Task | Not started
SU-S0-02 | S0 Gates and decisions | Gate C: decide how the Iceberg runtime, the S3 access bundle (S3A + matching AWS SDK, or Iceberg AWS bundle) and the Postgres JDBC driver reach the driver and every executor (baked in vs resolved at runtime). | Task | Not started
SU-S0-03 | S0 Gates and decisions | Gate D: choose the catalog (recommended: JDBC on Postgres, separate database). Record in Decisions. | Task | Not started
SU-S0-04 | S0 Gates and decisions | Gate E: plan Postgres capacity for ~34M order lines (disk, memory, bulk load then index) and decide what stays in Postgres vs files only. | Task | Not started
SU-S0-05 | S0 Gates and decisions | Set explicit CPU and memory limits on Postgres and RustFS (or record that you left them off on purpose). | Task | Not started
S1 Platform bring-up
SU-S1-01 | S1 Platform bring-up | 1. RustFS running (pinned release tag, changed credentials). Log in to the console, create buckets landing, warehouse, checkpoints, spark-events, archive; list them with an S3 client. | Task | Not started
SU-S1-02 | S1 Platform bring-up | 2. PostgreSQL running with two databases (source, catalog). Connect from your laptop and from the Jupyter container. | Task | Not started
SU-S1-03 | S1 Platform bring-up | 3. Spark cluster running. Master UI shows 4 workers, each with 2 cores and 2 GB. | Task | Not started
SU-S1-04 | S1 Platform bring-up | 4. Jars resolved. A session starts with the Iceberg runtime, S3 access and the JDBC driver on the driver and on executors. | Task | Not started
SU-S1-05 | S1 Platform bring-up | 5. Catalog configured. Create and drop a test namespace. | Task | Not started
SU-S1-06 | S1 Platform bring-up | 6. Iceberg smoke test. Create a table, insert, read back, list snapshots, and see data and metadata objects in the RustFS console. | Task | Not started
SU-S1-07 | S1 Platform bring-up | 7. S3A smoke test. Write and read Parquet at an s3a path and compare with Iceberg's own file I/O. | Task | Not started
SU-S1-08 | S1 Platform bring-up | 8. JDBC smoke test. Read a 1M-row test table with several partitions and watch the connections in Postgres. | Task | Not started
SU-S1-09 | S1 Platform bring-up | 9. History server shows a finished application with its event log in the bucket. | Task | Not started
SU-S1-10 | S1 Platform bring-up | 10. End-to-end hello pipeline: Postgres -> landing Parquet -> Iceberg bronze -> query. Run twice; the second run must be idempotent. | Task | Not started
S2 RustFS smoke tests
SU-S2-01 | S2 RustFS smoke tests | Write and read a Parquet file through both S3A and Iceberg file I/O. | Experiment | Not started
SU-S2-02 | S2 RustFS smoke tests | Write an object larger than the multipart threshold. | Experiment | Not started
SU-S2-03 | S2 RustFS smoke tests | List a prefix with 10k+ objects (note time and pagination). | Experiment | Not started
SU-S2-04 | S2 RustFS smoke tests | Delete many objects (cleanup and orphan removal path). | Experiment | Not started
SU-S2-05 | S2 RustFS smoke tests | Two Spark applications writing at once. | Experiment | Not started
SU-S2-06 | S2 RustFS smoke tests | Read an Iceberg table's metadata tables. | Experiment | Not started
SU-S2-07 | S2 RustFS smoke tests | Kill RustFS during a write, restart, verify table and objects. | Experiment | Not started
SU-S2-08 | S2 RustFS smoke tests | Smoke-test results recorded; every difference from AWS S3 behavior noted. | Exit check | Not started
S3 Dataset acquisition
SU-S3-01 | S3 Dataset acquisition | Create a Kaggle account and accept the Instacart competition rules so the files unlock. | Task | Not started
SU-S3-02 | S3 Dataset acquisition | Read the dataset terms (learning use only; keep your copy out of shared repositories). | Task | Not started
SU-S3-03 | S3 Dataset acquisition | Download all files and record checksums. | Task | Not started
SU-S3-04 | S3 Dataset acquisition | Store an immutable copy under landing/raw_dump. | Task | Not started
SU-S3-05 | S3 Dataset acquisition | Record file sizes and plain line counts (your first reconciliation numbers). | Task | Not started
SU-S3-06 | S3 Dataset acquisition | Raw files stored untouched, with checksums and line counts written down. | Exit check | Not started
S4 Helpers
SU-S4-01 | S4 Helpers | Dataset loader (stage as text, type, constrain, log violations to the defect register). | Task | Not started
SU-S4-02 | S4 Helpers | Timeline builder (rebuild timestamps from gaps, hours, weekdays; report inconsistencies). | Task | Not started
SU-S4-03 | S4 Helpers | Enricher (users, stores, price book, totals, payments, lifecycle). | Task | Not started
SU-S4-04 | S4 Helpers | Sampler / upscaler (reproducible S, M, L tiers). | Task | Not started
SU-S4-05 | S4 Helpers | Lifecycle replayer (change simulator with adjustable speed and late-change probability). | Task | Not started
SU-S4-06 | S4 Helpers | Clickstream generator (continuous and bulk JSON sessions to landing). | Task | Not started
SU-S4-07 | S4 Helpers | Session factory (master, driver host, catalog, S3 settings, event-log location, per-experiment overrides). | Task | Not started
SU-S4-08 | S4 Helpers | Timer and job labeler. | Task | Not started
SU-S4-09 | S4 Helpers | No-op executor (forces full execution without a write). | Task | Not started
SU-S4-10 | S4 Helpers | Plan reporter (scan filters, join types, exchange counts). | Task | Not started
SU-S4-11 | S4 Helpers | Iceberg inspector (files, sizes, snapshots, manifests from metadata tables). | Task | Not started
SU-S4-12 | S4 Helpers | Reconciler (counts and checksums across source, bronze, silver, gold). | Task | Not started
S5 Conventions
SU-S5-01 | S5 Conventions | Keep the Defect register, Experiment log and Decision log current (tabs in this workbook). | Task | Not started
SU-S5-02 | S5 Conventions | Decide run id and extract id conventions carried into every layer. | Task | Not started
SU-S5-03 | S5 Conventions | Decide namespaces (bronze, silver, gold, quarantine) and the landing path convention (source / table / extract date / extract id). | Task | Not started
SU-S5-04 | S5 Conventions | Fix random seeds for every generator so any tier can be rebuilt identically. | Task | Not started
SU-S5-05 | S5 Conventions | Decide time-zone policy: store UTC, document the assumed local zone for the rebuilt timeline. | Task | Not started
SU-S5-06 | S5 Conventions | All gates decided, all 10 bring-up steps verified, helpers usable, conventions written down. | Exit check | Not started

## P1_ETL
Project 1: Lakehouse medallion ETL
Source: 01-lakehouse-medallion-etl.md. Edit only the yellow cells: Status (dropdown), Started, Completed, Evidence / notes.
Progress | 0% | 0 of 113 items done ¦ In progress: 0 ¦ Blocked: 0 ¦ Skipped: 0
ID | Milestone | Task | Type | Status | Started | Completed | Evidence / notes
M0 Load, profile, enrich
P1-M0-01 | M0 Load, profile, enrich | Keep an untouched copy of the raw files in landing/raw_dump (everything must be reproducible from it). | Task | Not started
P1-M0-02 | M0 Load, profile, enrich | Create a staging schema with every column as text; load all files; note rows per second for each loading method. | Task | Not started
P1-M0-03 | M0 Load, profile, enrich | Fix CSV parsing of product names (commas, quotes): naive reader vs quoted-CSV reader; log the broken-row count as a defect. | Task | Not started
P1-M0-04 | M0 Load, profile, enrich | Type the data in a second step; capture every row that fails to cast. | Task | Not started
P1-M0-05 | M0 Load, profile, enrich | Profile every table: row count, null rate, distinct counts, min/max, text lengths, top values, duplicate rate on candidate keys. | Task | Not started
P1-M0-06 | M0 Load, profile, enrich | Profile relationships (orphan counts per candidate foreign key, cardinality), distributions (basket size, orders per user, product frequency, hour/weekday) and temporal fields (days_since_prior_order, spike at the cap, nulls by order_number). | Task | Not started
P1-M0-07 | M0 Load, profile, enrich | Union prior and train lines into one table with a source-file column; decide and record how test-set orders (no lines) are represented. | Task | Not started
P1-M0-08 | M0 Load, profile, enrich | Add constraints in stages (PKs on small tables and orders, composite PK on lines, FKs lines->orders/products, products->aisles/departments); fill the constraint status table with violation counts. | Task | Not started
P1-M0-09 | M0 Load, profile, enrich | Verify the reordered flag against each user's history; interpret mismatches. | Task | Not started
P1-M0-10 | M0 Load, profile, enrich | Build the rebuilt timeline (start date, first order, capped gaps, weekday mismatch rules); output timestamp and quality flag; report the weekday-fit rate. | Task | Not started
P1-M0-11 | M0 Load, profile, enrich | Generate synthetic tables in dependency order: users, stores, price book, totals, payments, lifecycle, erasures, campaign calendar; test each with its validity rules. | Task | Not started
P1-M0-12 | M0 Load, profile, enrich | Add updated_at and is_deleted, keys and FK indexes; deliberately skip one useful index (for example on the order timestamp). | Task | Not started
P1-M0-13 | M0 Load, profile, enrich | Install change-log triggers after the bulk load. | Task | Not started
P1-M0-14 | M0 Load, profile, enrich | Build tiers: S (sample by user), then M; re-profile and compare distributions with M. | Task | Not started
P1-M0-15 | M0 Load, profile, enrich | Loading methods: server-side copy vs client-side copy vs Spark JDBC write. | Experiment | Not started
P1-M0-16 | M0 Load, profile, enrich | Index and constraint timing: before load vs after load (total load time). | Experiment | Not started
P1-M0-17 | M0 Load, profile, enrich | Lines table design in Postgres: single table vs partitioned by order date. | Experiment | Not started
P1-M0-18 | M0 Load, profile, enrich | Test-set orders: keep vs flag vs separate table. | Experiment | Not started
P1-M0-19 | M0 Load, profile, enrich | Defect register covers every issue in README section 3.3; constraint table complete; timeline report written; S and M row counts match the files. | Exit check | Not started
M1 Full extraction
P1-M1-01 | M1 Full extraction | Choose the snapshot-consistency approach per table (shared repeatable-read snapshot, quiet window, or accept and reconcile). | Task | Not started
P1-M1-02 | M1 Full extraction | Choose a partitioning strategy per table (id ranges, hash, month, surrogate key); get bounds from a min/max query just before the run. | Task | Not started
P1-M1-03 | M1 Full extraction | Measure rows per partition before the full run (large baskets make equal id ranges unequal). | Task | Not started
P1-M1-04 | M1 Full extraction | Run the extract at a modest partition count, then scale up. | Task | Not started
P1-M1-05 | M1 Full extraction | Land to a temporary location with the path convention, then publish a manifest last (table, extract id, rows, bytes, partitions, timestamps, snapshot id). | Task | Not started
P1-M1-06 | M1 Full extraction | Validate row counts and a column checksum against Postgres. | Task | Not started
P1-M1-07 | M1 Full extraction | Partition count sweep: 1, 4, 8, 16, 32 (time, Postgres connections, slowest task). | Experiment | Not started
P1-M1-08 | M1 Full extraction | fetchsize sweep: small / default / large (executor memory, round trips). | Experiment | Not started
P1-M1-09 | M1 Full extraction | Table option vs query with a subquery (what Postgres actually executes). | Experiment | Not started
P1-M1-10 | M1 Full extraction | Landing format and compression: Parquet / CSV / JSON x snappy / zstd / none. | Experiment | Not started
P1-M1-11 | M1 Full extraction | Output file size: many small vs few large files (later scan cost on RustFS). | Experiment | Not started
P1-M1-12 | M1 Full extraction | Partition on the unindexed timestamp and observe the effect of the missing index. | Experiment | Not started
P1-M1-13 | M1 Full extraction | All tables extracted with matching counts and checksums; manifest per extract; partition choices justified with evidence. | Exit check | Not started
M2 Incremental extraction
P1-M2-01 | M2 Incremental extraction | Start the lifecycle replayer so Postgres changes continuously. | Task | Not started
P1-M2-02 | M2 Incremental extraction | Choose an extraction strategy per table (watermark on updated_at, monotonic key, change-log polling, snapshot diff) and justify each. | Task | Not started
P1-M2-03 | M2 Incremental extraction | Build the control table: run id, lower/upper bound, status, row counts, start/finish times. | Task | Not started
P1-M2-04 | M2 Incremental extraction | Measure real update lateness and set the overlap window from data. | Task | Not started
P1-M2-05 | M2 Incremental extraction | Extract the window, land with run id, deduplicate on key and latest change. | Task | Not started
P1-M2-06 | M2 Incremental extraction | Implement delete detection (soft-delete flag, tombstones in the change log, periodic full key reconciliation). | Task | Not started
P1-M2-07 | M2 Incremental extraction | Prove idempotency: re-run the same window; fail a run midway and recover on the next run. | Task | Not started
P1-M2-08 | M2 Incremental extraction | Reconcile counts and key sets between source and landing at intervals. | Task | Not started
P1-M2-09 | M2 Incremental extraction | Compare strategies: watermark vs change-log polling vs snapshot diff (cost, missed changes). | Experiment | Not started
P1-M2-10 | M2 Incremental extraction | Compare delete detection: flag, tombstone, reconciliation, flag + reconciliation. | Experiment | Not started
P1-M2-11 | M2 Incremental extraction | A day of replayed changes arrives complete; no missed late updates; hard deletes detected within the documented lag. | Exit check | Not started
M3 Bronze
P1-M3-01 | M3 Bronze | Define the bronze contract: raw as received plus lineage columns (run id, extract id, source system, ingested time, source file, operation). | Task | Not started
P1-M3-02 | M3 Bronze | Create one bronze table per source table (snapshot and incremental loads together). | Task | Not started
P1-M3-03 | M3 Bronze | Decide typed vs all-string bronze and record it. | Task | Not started
P1-M3-04 | M3 Bronze | Choose table properties: format version, file format, compression, target file size. | Task | Not started
P1-M3-05 | M3 Bronze | Choose partitioning for the lines table; predict file counts, then verify with the metadata tables. | Task | Not started
P1-M3-06 | M3 Bronze | Load from landing; load clickstream with an explicit schema, corrupt-record capture and the planned schema drift handled. | Task | Not started
P1-M3-07 | M3 Bronze | After every write inspect snapshots, files, manifests, partitions and compare with the RustFS objects. | Task | Not started
P1-M3-08 | M3 Bronze | Sanity-check: counts match landing manifests; trace sample rows back to source. | Task | Not started
P1-M3-09 | M3 Bronze | Lines partitioning: month of order date / day of load / bucket on order id / department / unpartitioned sorted. | Experiment | Not started
P1-M3-10 | M3 Bronze | Two compression codecs and two target file sizes. | Experiment | Not started
P1-M3-11 | M3 Bronze | Typed vs all-string bronze; one table vs two tables for snapshots and increments. | Experiment | Not started
P1-M3-12 | M3 Bronze | All bronze tables reconciled with landing; each partition choice evaluated with file counts and sizes; lineage complete. | Exit check | Not started
M4 Silver
P1-M4-01 | M4 Silver | Order lines: dedupe on order + product; validate add_to_cart_order is gap-free; flag orders without lines; join the price valid at order time. | Task | Not started
P1-M4-02 | M4 Silver | Orders: validate user history (contiguous, unique order numbers); keep raw eval_set; apply timeline; flag cancelled; quarantine impossible lifecycles. | Task | Not started
P1-M4-03 | M4 Silver | Products and taxonomy: conform three levels; explicit unknown for the placeholder aisle/department; normalize names. | Task | Not started
P1-M4-04 | M4 Silver | Users SCD2: valid_from / valid_to / is_current for membership tier; prove with as-of queries. | Task | Not started
P1-M4-05 | M4 Silver | Prices: effective-dated; detect overlaps and gaps; resolve promotions by precedence. | Task | Not started
P1-M4-06 | M4 Silver | Payments: reconcile against priced lines + fees + tip; classify mismatches. | Task | Not started
P1-M4-07 | M4 Silver | Reorder flag: rebuild from history; compare with the source flag; quarantine or flag disagreements. | Task | Not started
P1-M4-08 | M4 Silver | Clickstream: dedupe on event id; handle late events; map sessions to orders; quarantine malformed events. | Task | Not started
P1-M4-09 | M4 Silver | MERGE design for every current-state table: match key, newer-wins rule, collapse the batch first, delete handling. | Task | Not started
P1-M4-10 | M4 Silver | Prove MERGE idempotency (apply the same batch twice). | Task | Not started
P1-M4-11 | M4 Silver | Build quarantine tables with a reason-code catalog and rule version; decide reject / flag / count per rule. | Task | Not started
P1-M4-12 | M4 Silver | Build and run the data-quality rule catalog (completeness, validity, uniqueness, referential, consistency, timeliness); store metrics per run. | Task | Not started
P1-M4-13 | M4 Silver | Copy-on-write vs merge-on-read at 0.1%, 1%, 10% updates (write time, read time, delete files). | Experiment | Not started
P1-M4-14 | M4 Silver | SCD2 build: MERGE in steps vs build changed rows then insert. | Experiment | Not started
P1-M4-15 | M4 Silver | Price join: range join vs daily-expanded price table. | Experiment | Not started
P1-M4-16 | M4 Silver | Dedup: arbitrary row vs deterministic latest. | Experiment | Not started
P1-M4-17 | M4 Silver | Casting: strict (fail) vs try_* with quarantine. | Experiment | Not started
P1-M4-18 | M4 Silver | Row accounting balances (bronze = silver + quarantined + deduplicated); SCD2 as-of queries correct; merges idempotent. | Exit check | Not started
M5 Gold
P1-M5-01 | M5 Gold | Write grain, inputs, pitfalls and invariants for every mart before building. | Task | Not started
P1-M5-02 | M5 Gold | Mart: reorder rate by product, aisle, department (exclude orders with no lines; define denominators). | Task | Not started
P1-M5-03 | M5 Gold | Mart: basket analytics (items per order, department mix, add-to-cart position vs reorder). | Task | Not started
P1-M5-04 | M5 Gold | Mart: order cadence (gap distribution with capped gaps as censored; hour by weekday). | Task | Not started
P1-M5-05 | M5 Gold | Mart: user 360 (recency, frequency, monetary; favorites; department vector). | Task | Not started
P1-M5-06 | M5 Gold | Mart: cohorts (first-order month by order number; incomplete months). | Task | Not started
P1-M5-07 | M5 Gold | Mart: top-N products per department per month (deterministic ties). | Task | Not started
P1-M5-08 | M5 Gold | Mart: product co-occurrence (decide pruning and basket caps; see Project 2). | Task | Not started
P1-M5-09 | M5 Gold | Mart: next-basket features (as-of date, last N orders, no leakage). | Task | Not started
P1-M5-10 | M5 Gold | Choose a refresh strategy per mart: full rebuild, partition overwrite, MERGE, delete + insert. | Task | Not started
P1-M5-11 | M5 Gold | Run each refresh strategy twice and diff the outputs (idempotency). | Experiment | Not started
P1-M5-12 | M5 Gold | Layout: partition by date vs department; bucket by user; pre-aggregate; cache a shared input; sort order. | Experiment | Not started
P1-M5-13 | M5 Gold | Every mart has a documented grain and passing invariants; three refresh strategies tried on one mart; reruns identical. | Exit check | Not started
M6 Evolution and WAP
P1-M6-01 | M6 Evolution and WAP | Time travel by snapshot id and by timestamp; compare a gold number before and after a load. | Task | Not started
P1-M6-02 | M6 Evolution and WAP | Load wrong data on purpose (for example a mis-versioned price book), detect it, roll back; record what was rolled back. | Task | Not started
P1-M6-03 | M6 Evolution and WAP | Schema evolution matrix: add nullable column, add with default meaning, rename, drop, widen a type, reorder; check old and new readers. | Task | Not started
P1-M6-04 | M6 Evolution and WAP | Partition evolution on lines (monthly -> daily): confirm old files unchanged; read plans across both specs; decide on rewrite. | Task | Not started
P1-M6-05 | M6 Evolution and WAP | Branch and tag: stage a load on a branch, run the DQ suite, publish only if checks pass; tag month-end snapshots. | Task | Not started
P1-M6-06 | M6 Evolution and WAP | Define snapshot and tag retention policy. | Task | Not started
P1-M6-07 | M6 Evolution and WAP | A rollback restored a clean state; every evolution type has a recorded outcome; a failing check blocked a publish. | Exit check | Not started
M7 Maintenance
P1-M7-01 | M7 Maintenance | Baseline: file counts and sizes, manifest, snapshot and delete-file counts, scan time of three reference queries. | Task | Not started
P1-M7-02 | M7 Maintenance | Create the mess (tiny appends, many merges producing delete files, many snapshots); re-measure. | Task | Not started
P1-M7-03 | M7 Maintenance | Compaction: bin-pack vs sort vs z-order; target size; minimum input files. | Experiment | Not started
P1-M7-04 | M7 Maintenance | Manifest rewrite: effect on planning time. | Experiment | Not started
P1-M7-05 | M7 Maintenance | Delete-file compaction after merge-on-read. | Experiment | Not started
P1-M7-06 | M7 Maintenance | Snapshot expiry: retention age and minimum snapshots kept (time travel lost vs storage returned). | Experiment | Not started
P1-M7-07 | M7 Maintenance | Orphan removal: age threshold and safety with in-flight writes. | Experiment | Not started
P1-M7-08 | M7 Maintenance | Order the actions into a schedule and test it with a writer running. | Task | Not started
P1-M7-09 | M7 Maintenance | Write the runbook: cadence, triggers, safety rules, alerts. | Task | Not started
P1-M7-10 | M7 Maintenance | Each action has a measured benefit; the schedule survives a concurrent writer; runbook written. | Exit check | Not started
M8 Orchestration and reconciliation
P1-M8-01 | M8 Orchestration and reconciliation | Draw the dependency graph; choose run ordering and retry rules. | Task | Not started
P1-M8-02 | M8 Orchestration and reconciliation | Rerun tests: one day end to end, a failed middle step, a backfill of a past day (identical results). | Task | Not started
P1-M8-03 | M8 Orchestration and reconciliation | Drill: kill a worker mid-write (no duplicate or partial data). | Experiment | Not started
P1-M8-04 | M8 Orchestration and reconciliation | Drill: stop RustFS mid-commit (table unchanged; list leftover files). | Experiment | Not started
P1-M8-05 | M8 Orchestration and reconciliation | Drill: stop Postgres mid-extract (no half-published extract; manifest absent). | Experiment | Not started
P1-M8-06 | M8 Orchestration and reconciliation | Drill: kill the driver mid-merge (rerun applies exactly once). | Experiment | Not started
P1-M8-07 | M8 Orchestration and reconciliation | Drill: corrupt a landing file (quarantine path; pipeline continues). | Experiment | Not started
P1-M8-08 | M8 Orchestration and reconciliation | Reconciliation report across raw files, Postgres, landing, bronze, silver, gold (counts, key sets, totals); tie every difference to a defect-register entry. | Task | Not started
P1-M8-09 | M8 Orchestration and reconciliation | List what to automate, monitor and alert on. | Task | Not started
P1-M8-10 | M8 Orchestration and reconciliation | Every drill outcome matches prediction (or the surprise is explained); reconciliation has zero unexplained differences. | Exit check | Not started

## P2_Joins
Project 2: Joins, shuffles and skew
Source: 02-joins-shuffle-skew.md. Edit only the yellow cells: Status (dropdown), Started, Completed, Evidence / notes.
Progress | 0% | 0 of 91 items done ¦ In progress: 0 ¦ Blocked: 0 ¦ Skipped: 0
ID | Milestone | Task | Type | Status | Started | Completed | Evidence / notes
M0 Test bed and baselines
P2-M0-01 | M0 Test bed and baselines | Freeze the data version: record Iceberg snapshot ids of lines, orders, products, aisles, departments, users, stores, price book, payments, events. | Task | Not started
P2-M0-02 | M0 Test bed and baselines | Define benchmark queries J1-J8 (reorder rate by dept/aisle; orders by store/day; revenue per store/day; top-10 products per user; co-occurrence; price range join; payments reconciliation; lake x Postgres). | Task | Not started
P2-M0-03 | M0 Test bed and baselines | Profile keys: share of rows held by top 1/10/100 keys (product, aisle, department, store, user, hour/weekday, basket size). | Task | Not started
P2-M0-04 | M0 Test bed and baselines | Build table variants: lines partitioned by month; lines and orders bucketed on order id (several bucket counts); compacted copies. | Task | Not started
P2-M0-05 | M0 Test bed and baselines | Record baselines: run J1-J8 with defaults twice; log time, shuffle bytes, spill, tasks, plan fingerprint. | Task | Not started
P2-M0-06 | M0 Test bed and baselines | Every query has a baseline and plan; key-skew table exists; variants compacted. | Exit check | Not started
M1 Reading baseline plans
P2-M1-01 | M1 Reading baseline plans | Annotate J1-J4 plans: scan, pushed filters, join type, exchange, sort, partial/final aggregate. | Task | Not started
P2-M1-02 | M1 Reading baseline plans | Predict join types and reasons before checking the plan. | Task | Not started
P2-M1-03 | M1 Reading baseline plans | Force sort-merge (disable auto-broadcast and AQE); count exchanges and sorts; compare time. | Task | Not started
P2-M1-04 | M1 Reading baseline plans | Re-enable AQE; find runtime changes in the final plan. | Task | Not started
P2-M1-05 | M1 Reading baseline plans | Note how Iceberg scans appear and which filters are pushed. | Task | Not started
P2-M1-06 | M1 Reading baseline plans | At least 80% of join-type predictions correct; mismatches explained. | Exit check | Not started
M2 Join strategies by hint
P2-M2-01 | M2 Join strategies by hint | Force broadcast, sort-merge and shuffle-hash on product/aisle/department joins; compare. | Task | Not started
P2-M2-02 | M2 Join strategies by hint | Find the largest broadcastable table given driver memory and broadcast timeout. | Task | Not started
P2-M2-03 | M2 Join strategies by hint | Compare shuffle-hash vs sort-merge where the build side fits (time, memory per task, spill). | Task | Not started
P2-M2-04 | M2 Join strategies by hint | Try the nested-loop hint on tiny inputs only. | Task | Not started
P2-M2-05 | M2 Join strategies by hint | Broadcast side sizes: 50k, 1M, 5M rows. | Experiment | Not started
P2-M2-06 | M2 Join strategies by hint | Auto-broadcast threshold: disabled / 10 MB / 100 MB. | Experiment | Not started
P2-M2-07 | M2 Join strategies by hint | Swap the build side by table order or hint. | Experiment | Not started
P2-M2-08 | M2 Join strategies by hint | Best strategy per query with its margin over the default. | Exit check | Not started
M3 Federated joins
P2-M3-01 | M3 Federated joins | Run J8 (lake lines x Postgres products and price book); read what was pushed vs pulled. | Task | Not started
P2-M3-02 | M3 Federated joins | Run it twice and confirm Postgres is hit again each time. | Task | Not started
P2-M3-03 | M3 Federated joins | Cached JDBC read. | Experiment | Not started
P2-M3-04 | M3 Federated joins | Broadcast the JDBC read. | Experiment | Not started
P2-M3-05 | M3 Federated joins | Snapshot the Postgres tables into Iceberg first. | Experiment | Not started
P2-M3-06 | M3 Federated joins | Join inside Postgres via a pushed-down subquery. | Experiment | Not started
P2-M3-07 | M3 Federated joins | Observe Postgres connections, queries, load, locks; test selective vs unselective cases. | Task | Not started
P2-M3-08 | M3 Federated joins | Break-even rule written (queries per hour, data volume) for each approach. | Exit check | Not started
M4 Diagnosing skew
P2-M4-01 | M4 Diagnosing skew | Aggregate and join on product, department, aisle, store, hour and the bulk buyer; record min/median/max task time, slowest-task shuffle read vs median, spill. | Task | Not started
P2-M4-02 | M4 Diagnosing skew | Show skew in four places: a join, a window by user, a MERGE with a hot source key, uneven JDBC partitions. | Task | Not started
P2-M4-03 | M4 Diagnosing skew | Contrast high-cardinality skew (hot product) with low-cardinality skew (21 departments): idle partitions. | Task | Not started
P2-M4-04 | M4 Diagnosing skew | Write the skew checklist (UI signals + key-profile signals). | Task | Not started
P2-M4-05 | M4 Diagnosing skew | Cause identified from the UI alone in all four cases. | Exit check | Not started
M5 Skew-fix ladder
P2-M5-01 | M5 Skew-fix ladder | AQE skew handling: lower thresholds, find skew markers, note where it does not apply. | Experiment | Not started
P2-M5-02 | M5 Skew-fix ladder | Salting with factors 4, 8, 32 (joins; two-phase aggregations). | Experiment | Not started
P2-M5-03 | M5 Skew-fix ladder | Hot-key isolation: broadcast top K keys, shuffle the rest, union. | Experiment | Not started
P2-M5-04 | M5 Skew-fix ladder | Pre-aggregation to product-and-day grain. | Experiment | Not started
P2-M5-05 | M5 Skew-fix ladder | Denormalize the dimension into the lines table. | Experiment | Not started
P2-M5-06 | M5 Skew-fix ladder | Repeat the best fixes for an aggregation and for a MERGE. | Task | Not started
P2-M5-07 | M5 Skew-fix ladder | Build the comparison table: time, max/median ratio, shuffle bytes, spill, complexity. | Task | Not started
P2-M5-08 | M5 Skew-fix ladder | Chosen fix for a join, an aggregation and a MERGE, each with evidence. | Exit check | Not started
M6 Pair explosion
P2-M6-01 | M6 Pair explosion | Predict the pair count from the basket-size distribution. | Task | Not started
P2-M6-02 | M6 Pair explosion | Check on a small sample; measure at M if feasible. | Task | Not started
P2-M6-03 | M6 Pair explosion | Explain why a few huge baskets dominate pair counts, shuffle size and spill. | Task | Not started
P2-M6-04 | M6 Pair explosion | Cap or sample huge baskets. | Experiment | Not started
P2-M6-05 | M6 Pair explosion | Prune to frequent products before pairing. | Experiment | Not started
P2-M6-06 | M6 Pair explosion | Canonical pair order (halve the work). | Experiment | Not started
P2-M6-07 | M6 Pair explosion | Partial pre-aggregation per pair. | Experiment | Not started
P2-M6-08 | M6 Pair explosion | Split by department and combine. | Experiment | Not started
P2-M6-09 | M6 Pair explosion | Mark each fix: changes the answer vs changes only the plan. | Task | Not started
P2-M6-10 | M6 Pair explosion | Same top pairs from at least two methods, with documented cost and accuracy difference. | Exit check | Not started
M7 Range joins
P2-M7-01 | M7 Range joins | Price each line from the effective-dated price book; record the join type. | Task | Not started
P2-M7-02 | M7 Range joins | Expanded daily price table + equi-join. | Experiment | Not started
P2-M7-03 | M7 Range joins | Time-bucket (weeks) join then filter. | Experiment | Not started
P2-M7-04 | M7 Range joins | Sorted as-of lookup. | Experiment | Not started
P2-M7-05 | M7 Range joins | Broadcast the price book. | Experiment | Not started
P2-M7-06 | M7 Range joins | Repeat with the campaign calendar. | Task | Not started
P2-M7-07 | M7 Range joins | Test at M, then L; verify identical results on a sample. | Task | Not started
P2-M7-08 | M7 Range joins | One approach runs in reasonable time at L with verified identical results. | Exit check | Not started
M8 Partition sizing and writes
P2-M8-01 | M8 Partition sizing and writes | AQE off: sweep shuffle partitions 8 to 1000 on J1, J3, J4 and plot time. | Task | Not started
P2-M8-02 | M8 Partition sizing and writes | AQE on: vary advisory size 16 MB to 256 MB; find coalesced reads in the plan. | Task | Not started
P2-M8-03 | M8 Partition sizing and writes | Write distribution modes none / hash / range (shuffle cost, files per partition, file sizes). | Experiment | Not started
P2-M8-04 | M8 Partition sizing and writes | Write down how shuffle partitions x distribution mode x table partitioning decide output file count; test it. | Task | Not started
P2-M8-05 | M8 Partition sizing and writes | You can predict the file count of a write before running it. | Exit check | Not started
M9 Storage-partitioned joins
P2-M9-01 | M9 Storage-partitioned joins | Build orders and lines bucketed identically on order id (same bucket count). | Task | Not started
P2-M9-02 | M9 Storage-partitioned joins | Enable the required Spark and Iceberg settings (check docs for your version). | Task | Not started
P2-M9-03 | M9 Storage-partitioned joins | Confirm no exchange on either side; compare time with a regular join. | Task | Not started
P2-M9-04 | M9 Storage-partitioned joins | Break it: different bucket counts. | Experiment | Not started
P2-M9-05 | M9 Storage-partitioned joins | Break it: extra partition column. | Experiment | Not started
P2-M9-06 | M9 Storage-partitioned joins | Break it: different join key. | Experiment | Not started
P2-M9-07 | M9 Storage-partitioned joins | Break it: one side unbucketed. | Experiment | Not started
P2-M9-08 | M9 Storage-partitioned joins | Compare with Hive-style bucketing. | Experiment | Not started
P2-M9-09 | M9 Storage-partitioned joins | Recommend a bucket count; note the design-time cost. | Task | Not started
P2-M9-10 | M9 Storage-partitioned joins | List of conditions under which the optimization applies. | Exit check | Not started
M10 Memory pressure and spill
P2-M10-01 | M10 Memory pressure and spill | Large sort / aggregation / merge with small executors and few partitions; record spill and GC. | Task | Not started
P2-M10-02 | M10 Memory pressure and spill | Fix: more partitions. | Experiment | Not started
P2-M10-03 | M10 Memory pressure and spill | Fix: fewer cores per executor. | Experiment | Not started
P2-M10-04 | M10 Memory pressure and spill | Fix: larger execution memory share. | Experiment | Not started
P2-M10-05 | M10 Memory pressure and spill | Fix: project early (narrower rows). | Experiment | Not started
P2-M10-06 | M10 Memory pressure and spill | Repeat for a MERGE; compare copy-on-write and merge-on-read memory behavior. | Task | Not started
P2-M10-07 | M10 Memory pressure and spill | Rank the fixes by effect per effort. | Task | Not started
P2-M10-08 | M10 Memory pressure and spill | Each spill explained and matched to the fix that addressed it. | Exit check | Not started
M11 Anti-pattern gallery
P2-M11-01 | M11 Anti-pattern gallery | Non-equi joins and joins on expressions (for example a normalized product name). | Task | Not started
P2-M11-02 | M11 Anti-pattern gallery | distinct before a join. | Task | Not started
P2-M11-03 | M11 Anti-pattern gallery | Cartesian product from a missing condition. | Task | Not started
P2-M11-04 | M11 Anti-pattern gallery | Whole-history window that could be bounded. | Task | Not started
P2-M11-05 | M11 Anti-pattern gallery | Unnecessary sort or repartition before a write. | Task | Not started
P2-M11-06 | M11 Anti-pattern gallery | Join key type mismatch causing casts. | Task | Not started
P2-M11-07 | M11 Anti-pattern gallery | Each pattern has plan, symptom and fix recorded. | Exit check | Not started
M12 Synthesis
P2-M12-01 | M12 Synthesis | Write the one-page decision tree (sizes, skew, join type, freshness -> strategy, settings, table design) with experiment ids. | Task | Not started
P2-M12-02 | M12 Synthesis | Predictions made before running; each fix has numbers; you can design a table to make a given join cheap. | Exit check | Not started

## P3_Planner
Project 3: Catalyst and query planning
Source: 03-catalyst-and-query-planning.md. Edit only the yellow cells: Status (dropdown), Started, Completed, Evidence / notes.
Progress | 0% | 0 of 79 items done ¦ In progress: 0 ¦ Blocked: 0 ¦ Skipped: 0
ID | Milestone | Task | Type | Status | Started | Completed | Evidence / notes
M0 Variants and query suite
P3-M0-01 | M0 Variants and query suite | Build lines/events variants: unsorted monthly-partitioned; sorted by product; z-ordered (department, hour); unpartitioned sorted; raw Parquet copy in landing. | Task | Not started
P3-M0-02 | M0 Variants and query suite | Compact every variant to the same target file size. | Task | Not started
P3-M0-03 | M0 Variants and query suite | Define Q1-Q12 (point lookup, low selectivity, date + hour, five-way join with selective dimension, bad join order, metadata-only aggregates, window by user, sampled pairs, price range join, JDBC filter + aggregate, UDF in filter, wide vs narrow select). | Task | Not started
P3-M0-04 | M0 Variants and query suite | Record baselines: time, bytes read, files scanned, plan fingerprint. | Task | Not started
P3-M0-05 | M0 Variants and query suite | All variants exist and are compacted; suite runs and is logged. | Exit check | Not started
M1 Plan literacy
P3-M1-01 | M1 Plan literacy | Predict Q1-Q4 plans (scan, pushed filters, joins, exchanges) before reading them. | Task | Not started
P3-M1-02 | M1 Plan literacy | Read parsed, analyzed, optimized and physical plans; compare with predictions. | Task | Not started
P3-M1-03 | M1 Plan literacy | Find constant folding, column pruning, predicate pushdown through a join, limit pushdown. | Task | Not started
P3-M1-04 | M1 Plan literacy | Learn every scan-node field (pushed, read, remaining). | Task | Not started
P3-M1-05 | M1 Plan literacy | Turn off one optimizer rule on a tiny sample; observe; restore. | Task | Not started
P3-M1-06 | M1 Plan literacy | Compare how Iceberg, JDBC and raw Parquet scans look in plans. | Task | Not started
P3-M1-07 | M1 Plan literacy | Learn plan formats: formatted, cost, codegen, SQL tab graph. | Task | Not started
P3-M1-08 | M1 Plan literacy | At least 80% of plan-feature predictions correct. | Exit check | Not started
M2 Iceberg pruning
P3-M2-01 | M2 Iceberg pruning | Q1/Q3 on the partitioned variant: confirm a timestamp filter prunes without naming a partition column (hidden partitioning). | Task | Not started
P3-M2-02 | M2 Iceberg pruning | Compare file-level skipping (min/max) across unsorted, sorted and z-ordered variants for equality and range filters. | Task | Not started
P3-M2-03 | M2 Iceberg pruning | Prove files and bytes scanned vs total with the metadata tables. | Task | Not started
P3-M2-04 | M2 Iceberg pruning | Compare planning vs execution time; build a many-manifest table to test. | Task | Not started
P3-M2-05 | M2 Iceberg pruning | Q6: can count, min and max be answered from metadata in your versions? | Task | Not started
P3-M2-06 | M2 Iceberg pruning | Q2: explain why pruning helps little for a low-selectivity filter. | Task | Not started
P3-M2-07 | M2 Iceberg pruning | Partition transform: month / day / bucket / none. | Experiment | Not started
P3-M2-08 | M2 Iceberg pruning | File size: small / target / large (planning time, RustFS requests). | Experiment | Not started
P3-M2-09 | M2 Iceberg pruning | Filter shapes: equality, range, IN list, OR. | Experiment | Not started
P3-M2-10 | M2 Iceberg pruning | For each query: files skipped, which metadata enabled it, how to improve it. | Exit check | Not started
M3 Runtime filtering
P3-M3-01 | M3 Runtime filtering | Q4 with a selective dimension filter; look for runtime partition pruning and bloom-filter runtime filters. | Task | Not started
P3-M3-02 | M3 Runtime filtering | Toggle each runtime filter setting; record rows scanned and time. | Experiment | Not started
P3-M3-03 | M3 Runtime filtering | Find when the filter is not inserted (non-selective, large build side, unsupported join, unpartitioned fact). | Task | Not started
P3-M3-04 | M3 Runtime filtering | Compare with a manual rewrite (explicit filter on the fact table). | Task | Not started
P3-M3-05 | M3 Runtime filtering | Conditions that trigger each runtime filter described for your tables. | Exit check | Not started
M4 Statistics and cost-based planning
P3-M4-01 | M4 Statistics and cost-based planning | Q5 with cost-based optimization off: record join order and time. | Task | Not started
P3-M4-02 | M4 Statistics and cost-based planning | Collect table and column statistics; enable CBO and join reordering; re-run. | Task | Not started
P3-M4-03 | M4 Statistics and cost-based planning | Read the cost plan; compare estimates with actuals; explain the worst misestimate. | Task | Not started
P3-M4-04 | M4 Statistics and cost-based planning | Histograms on a skewed column (department). | Experiment | Not started
P3-M4-05 | M4 Statistics and cost-based planning | Stale vs refreshed statistics after adding a day of data. | Experiment | Not started
P3-M4-06 | M4 Statistics and cost-based planning | Find which statistics Iceberg and Spark actually use in your versions. | Task | Not started
P3-M4-07 | M4 Statistics and cost-based planning | When CBO helped, when it hurt, and what upkeep it needs. | Exit check | Not started
M5 JDBC pushdown
P3-M5-01 | M5 JDBC pushdown | Equality or range filter on an indexed column: pushed? index used? | Experiment | Not started
P3-M5-02 | M5 JDBC pushdown | Same filter on the unindexed timestamp: sequential scan cost at M. | Experiment | Not started
P3-M5-03 | M5 JDBC pushdown | Aggregate over the table: pushed or pulled across? | Experiment | Not started
P3-M5-04 | M5 JDBC pushdown | Limit and offset: pushed? ordering issues. | Experiment | Not started
P3-M5-05 | M5 JDBC pushdown | Sampling: pushed? | Experiment | Not started
P3-M5-06 | M5 JDBC pushdown | Filter with a Spark-only function or UDF: why pushdown fails. | Experiment | Not started
P3-M5-07 | M5 JDBC pushdown | Cast on a filtered column: blocks index use? | Experiment | Not started
P3-M5-08 | M5 JDBC pushdown | Partitioned read with explicit predicates: does each partition hit an index? | Experiment | Not started
P3-M5-09 | M5 JDBC pushdown | Reading a view or arbitrary query: how aliasing changes planning. | Experiment | Not started
P3-M5-10 | M5 JDBC pushdown | For each case capture three views: Spark plan, SQL text Postgres received, Postgres execution plan. | Task | Not started
P3-M5-11 | M5 JDBC pushdown | Toggle each pushdown option; record rows transferred and time. | Task | Not started
P3-M5-12 | M5 JDBC pushdown | Write the rule of thumb: logic in Postgres vs logic in Spark. | Task | Not started
P3-M5-13 | M5 JDBC pushdown | Pushdown matrix complete with evidence for every row. | Exit check | Not started
M6 AQE re-planning
P3-M6-01 | M6 AQE re-planning | Build a query where one side looks large at plan time but small after filtering; compare initial vs final plan. | Task | Not started
P3-M6-02 | M6 AQE re-planning | Record which AQE features fired (coalesce, local reader, skew, join switch). | Task | Not started
P3-M6-03 | M6 AQE re-planning | Disable each AQE feature in turn and measure. | Experiment | Not started
P3-M6-04 | M6 AQE re-planning | Find a case where AQE does not help. | Task | Not started
P3-M6-05 | M6 AQE re-planning | You can predict which AQE features fire for a given query. | Exit check | Not started
M7 Whole-stage codegen
P3-M7-01 | M7 Whole-stage codegen | Find the codegen stage markers in a filter, project and aggregate. | Task | Not started
P3-M7-02 | M7 Whole-stage codegen | Disable whole-stage codegen on a CPU-bound query and compare. | Experiment | Not started
P3-M7-03 | M7 Whole-stage codegen | 200+ column table: does codegen fall back? What does the plan show? | Experiment | Not started
P3-M7-04 | M7 Whole-stage codegen | Note operators that break codegen stages. | Task | Not started
P3-M7-05 | M7 Whole-stage codegen | Speed difference and fallback rule explained. | Exit check | Not started
M8 Optimizer blockers
P3-M8-01 | M8 Optimizer blockers | Python UDF inside a filter (Q11) -> rewrite with built-ins. | Experiment | Not started
P3-M8-02 | M8 Optimizer blockers | Expression on the filtered column (casts, formatting) -> sargable predicate. | Experiment | Not started
P3-M8-03 | M8 Optimizer blockers | OR across partition and non-partition columns -> split and union. | Experiment | Not started
P3-M8-04 | M8 Optimizer blockers | Non-deterministic function in a filter -> move after the join. | Experiment | Not started
P3-M8-05 | M8 Optimizer blockers | Cached table hides the scan -> cache only narrowed data. | Experiment | Not started
P3-M8-06 | M8 Optimizer blockers | Wide select into a wide join -> project early. | Experiment | Not started
P3-M8-07 | M8 Optimizer blockers | Many small files or manifests -> compact; rewrite manifests. | Experiment | Not started
P3-M8-08 | M8 Optimizer blockers | Self-join of lines for co-occurrence -> prune to frequent products and cap baskets. | Experiment | Not started
P3-M8-09 | M8 Optimizer blockers | Filter on an unindexed Postgres column -> add index or move work to the lake. | Experiment | Not started
P3-M8-10 | M8 Optimizer blockers | Join on a normalized product name -> normalize once in silver. | Experiment | Not started
P3-M8-11 | M8 Optimizer blockers | Range join to the price book -> expand to daily rows and equi-join. | Experiment | Not started
P3-M8-12 | M8 Optimizer blockers | Every pitfall has a measured before and after. | Exit check | Not started
M9 Layout optimization
P3-M9-01 | M9 Layout optimization | Sort order: product vs order date vs z-order for Q1, Q2, Q3, Q12. | Experiment | Not started
P3-M9-02 | M9 Layout optimization | Parquet settings: row-group size, page size, compression, dictionary encoding; column bloom filters for a high-cardinality lookup. | Experiment | Not started
P3-M9-03 | M9 Layout optimization | Format: Iceberg/Parquet vs ORC vs raw landing Parquet. | Experiment | Not started
P3-M9-04 | M9 Layout optimization | File size 32 MB vs 128 MB vs 512 MB (RustFS requests, planning time). | Experiment | Not started
P3-M9-05 | M9 Layout optimization | Compaction strategy: query speed per rewrite cost. | Experiment | Not started
P3-M9-06 | M9 Layout optimization | Capture RustFS request count and throughput per layout. | Task | Not started
P3-M9-07 | M9 Layout optimization | Layout recommended for point lookup, range scan and full scan, with numbers. | Exit check | Not started
M10 Synthesis
P3-M10-01 | M10 Synthesis | Write the one-page planner cheat sheet (reading each scan type, first checks, top ten blockers, top five layout rules) with experiment ids. | Task | Not started
P3-M10-02 | M10 Synthesis | You can read a plan and predict runtime behavior; every pruning and pushdown claim has evidence. | Exit check | Not started

## P4_Perf
Project 4: Executors, memory and I/O performance
Source: 04-executors-memory-io-performance.md. Edit only the yellow cells: Status (dropdown), Started, Completed, Evidence / notes.
Progress | 0% | 0 of 91 items done ¦ In progress: 0 ¦ Blocked: 0 ¦ Skipped: 0
ID | Milestone | Task | Type | Status | Started | Completed | Evidence / notes
M0 Workloads and baselines
P4-M0-01 | M0 Workloads and baselines | Define W1-W6: scan-heavy, shuffle-heavy, CPU-heavy (per-line score), memory-heavy (cache + wide aggregation), write-heavy (layout rewrite), mixed user-feature build. | Task | Not started
P4-M0-02 | M0 Workloads and baselines | Instrument every run with Spark UI, Iceberg metadata, RustFS, Postgres and host CPU/memory/disk. | Task | Not started
P4-M0-03 | M0 Workloads and baselines | Record baselines with the default layout, twice each. | Task | Not started
P4-M0-04 | M0 Workloads and baselines | Classify each workload by apparent bottleneck (to test later). | Task | Not started
P4-M0-05 | M0 Workloads and baselines | Each workload has a stable baseline (under 10% variation) and a first bottleneck guess. | Exit check | Not started
M1 Topology and strong scaling
P4-M1-01 | M1 Topology and strong scaling | Layout: 4 executors x (2 cores, 1 GB). | Experiment | Not started
P4-M1-02 | M1 Topology and strong scaling | Layout: 8 executors x (1 core, 1 GB). | Experiment | Not started
P4-M1-03 | M1 Topology and strong scaling | Layout: 4 executors x (2 cores, 2 GB). | Experiment | Not started
P4-M1-04 | M1 Topology and strong scaling | Layout: 8 executors x (1 core, 512 MB). | Experiment | Not started
P4-M1-05 | M1 Topology and strong scaling | Run W1-W4 on each layout; record time, spill, GC. | Task | Not started
P4-M1-06 | M1 Topology and strong scaling | Strong scaling with 1, 2, 4, 8 total cores; compute speedup and efficiency; find where it flattens. | Task | Not started
P4-M1-07 | M1 Topology and strong scaling | Diagnose the flat part: CPU-bound, storage-bound, source-bound or shuffle-bound. | Task | Not started
P4-M1-08 | M1 Topology and strong scaling | Compare best layout for shuffle-heavy vs scan-heavy; note memory per task. | Task | Not started
P4-M1-09 | M1 Topology and strong scaling | Scaling curve for each workload and a named bottleneck. | Exit check | Not started
M2 Memory model
P4-M2-01 | M2 Memory model | Read the Executors tab: storage memory, execution memory, GC time per task. | Task | Not started
P4-M2-02 | M2 Memory model | Run W4; record cached fraction, spill and GC share. | Task | Not started
P4-M2-03 | M2 Memory model | spark.memory.fraction: 0.4 / 0.6 / 0.8. | Experiment | Not started
P4-M2-04 | M2 Memory model | spark.memory.storageFraction: 0.2 / 0.5 / 0.8. | Experiment | Not started
P4-M2-05 | M2 Memory model | Off-heap memory: off vs on with a fixed size. | Experiment | Not started
P4-M2-06 | M2 Memory model | GC algorithm via executor Java options: default vs parallel. | Experiment | Not started
P4-M2-07 | M2 Memory model | Executor memory: 512m / 1g / 2g. | Experiment | Not started
P4-M2-08 | M2 Memory model | Cause an out-of-memory failure on purpose; learn its signature in the error and UI. | Task | Not started
P4-M2-09 | M2 Memory model | Note that memory overhead is not enforced in standalone; record the implication for YARN/Kubernetes. | Task | Not started
P4-M2-10 | M2 Memory model | From task metrics you can say whether memory, GC or spill is the issue and what to change. | Exit check | Not started
M3 Serialization and RDD
P4-M3-01 | M3 Serialization and RDD | Same aggregation: group-by-key vs reduce-by-key vs DataFrame (shuffle bytes, time). | Experiment | Not started
P4-M3-02 | M3 Serialization and RDD | Switch the serializer and explain why DataFrames barely change. | Experiment | Not started
P4-M3-03 | M3 Serialization and RDD | Persistence levels on an RDD and a DataFrame cache. | Experiment | Not started
P4-M3-04 | M3 Serialization and RDD | Shuffle compression codecs: lz4 / zstd / snappy on W2. | Experiment | Not started
P4-M3-05 | M3 Serialization and RDD | Shuffle buffer settings. | Experiment | Not started
P4-M3-06 | M3 Serialization and RDD | Rules for when RDD tricks help and when to stay with DataFrames. | Exit check | Not started
M4 Python UDF ladder
P4-M4-01 | M4 Python UDF ladder | Choose two per-row computations: math-heavy reorder-propensity score and product-name normalization + tokenization. | Task | Not started
P4-M4-02 | M4 Python UDF ladder | Rung 1: built-in functions. | Experiment | Not started
P4-M4-03 | M4 Python UDF ladder | Rung 2: SQL expressions and higher-order functions. | Experiment | Not started
P4-M4-04 | M4 Python UDF ladder | Rung 3: row-at-a-time Python UDF. | Experiment | Not started
P4-M4-05 | M4 Python UDF ladder | Rung 4: Arrow-optimized Python UDF. | Experiment | Not started
P4-M4-06 | M4 Python UDF ladder | Rung 5: pandas UDF. | Experiment | Not started
P4-M4-07 | M4 Python UDF ladder | Rung 6: map-in-Arrow or map-in-pandas. | Experiment | Not started
P4-M4-08 | M4 Python UDF ladder | Rung 7: RDD map. | Experiment | Not started
P4-M4-09 | M4 Python UDF ladder | Sweep Arrow batch size, Python worker memory limit, Python worker reuse. | Experiment | Not started
P4-M4-10 | M4 Python UDF ladder | Decompose time into JVM, serialization and Python where the UI allows. | Task | Not started
P4-M4-11 | M4 Python UDF ladder | Hot-key trap: grouped pandas computation per user overloads one worker (bulk buyer); fix with window functions or salting + two-phase. | Task | Not started
P4-M4-12 | M4 Python UDF ladder | Verify identical results across rungs within tolerance. | Task | Not started
P4-M4-13 | M4 Python UDF ladder | For any new transformation you can say which rung to start from and why. | Exit check | Not started
M5 Object-store tuning
P4-M5-01 | M5 Object-store tuning | Baseline W1 and W5; record RustFS request counts and throughput for full scan, filtered scan and write. | Task | Not started
P4-M5-02 | M5 Object-store tuning | S3A connection pool maximum. | Experiment | Not started
P4-M5-03 | M5 Object-store tuning | S3A thread pool size. | Experiment | Not started
P4-M5-04 | M5 Object-store tuning | S3A fast-upload buffering mode (disk / array / byte buffer). | Experiment | Not started
P4-M5-05 | M5 Object-store tuning | S3A multipart size and threshold. | Experiment | Not started
P4-M5-06 | M5 Object-store tuning | S3A block size and read-ahead. | Experiment | Not started
P4-M5-07 | M5 Object-store tuning | Access-pattern hint (sequential / random / adaptive). | Experiment | Not started
P4-M5-08 | M5 Object-store tuning | S3A vs Iceberg's own S3 file I/O for the same table. | Experiment | Not started
P4-M5-09 | M5 Object-store tuning | File size study: throughput vs file size; find where more size stops helping. | Experiment | Not started
P4-M5-10 | M5 Object-store tuning | Find the setting that governs Iceberg scan task size and sweep it. | Task | Not started
P4-M5-11 | M5 Object-store tuning | Watch for retry storms and timeouts under load (RustFS logs). | Task | Not started
P4-M5-12 | M5 Object-store tuning | Recommended storage settings and target file size, with evidence. | Exit check | Not started
M6 JDBC concurrency
P4-M6-01 | M6 JDBC concurrency | Read parallelism 1, 2, 4, 8, 16, 32: Postgres connections, CPU, latency, Spark time. | Experiment | Not started
P4-M6-02 | M6 JDBC concurrency | Find the point where Postgres hurts or Spark stops improving. | Task | Not started
P4-M6-03 | M6 JDBC concurrency | Explain how executors and cores bound connections and which Postgres limit applies. | Task | Not started
P4-M6-04 | M6 JDBC concurrency | Fetch size and executor memory behavior. | Experiment | Not started
P4-M6-05 | M6 JDBC concurrency | Write a gold aggregate back: batch size, batched-insert rewrite option, write parallelism (locks, WAL, indexes). | Experiment | Not started
P4-M6-06 | M6 JDBC concurrency | Staging table + swap vs writing into the live table. | Experiment | Not started
P4-M6-07 | M6 JDBC concurrency | Write the backpressure policy (max parallelism, quiet windows, read replica, or extract from the change log). | Task | Not started
P4-M6-08 | M6 JDBC concurrency | Maximum safe parallelism per Postgres workload stated with reasons. | Exit check | Not started
M7 Concurrent writers
P4-M7-01 | M7 Concurrent writers | Two appends at once (retry counts, commit time). | Experiment | Not started
P4-M7-02 | M7 Concurrent writers | Two merges touching the same files (error text). | Experiment | Not started
P4-M7-03 | M7 Concurrent writers | Merge vs compaction (who loses and why). | Experiment | Not started
P4-M7-04 | M7 Concurrent writers | Append during snapshot expiry. | Experiment | Not started
P4-M7-05 | M7 Concurrent writers | Write during orphan removal. | Experiment | Not started
P4-M7-06 | M7 Concurrent writers | Tune commit retries and isolation levels; compare serializable and snapshot isolation. | Task | Not started
P4-M7-07 | M7 Concurrent writers | Verify a failed commit leaves no visible partial data; measure orphan files. | Task | Not started
P4-M7-08 | M7 Concurrent writers | Write isolation rules: which jobs may run together and in what order. | Task | Not started
P4-M7-09 | M7 Concurrent writers | Table of safe and unsafe job combinations with a scheduling rule. | Exit check | Not started
M8 Scheduling and allocation
P4-M8-01 | M8 Scheduling and allocation | Dynamic allocation with shuffle tracking; sweep idle timeout and bounds. | Experiment | Not started
P4-M8-02 | M8 Scheduling and allocation | Two notebooks (two applications) concurrently: how standalone shares cores. | Experiment | Not started
P4-M8-03 | M8 Scheduling and allocation | FIFO vs FAIR scheduling with pools from separate threads. | Experiment | Not started
P4-M8-04 | M8 Scheduling and allocation | Data-locality wait sweep; does it matter with RustFS? | Experiment | Not started
P4-M8-05 | M8 Scheduling and allocation | Fair-sharing configuration described with numbers. | Exit check | Not started
M9 Resilience
P4-M9-01 | M9 Resilience | Straggler + speculation (multiplier, quantile); check for extra files in an Iceberg write. | Experiment | Not started
P4-M9-02 | M9 Resilience | Executor loss: kill a worker mid-job (task and stage retries, outcome, retry limits). | Experiment | Not started
P4-M9-03 | M9 Resilience | Storage failure: stop RustFS mid-write (errors, retries, table state, leftover files). | Experiment | Not started
P4-M9-04 | M9 Resilience | Source failure: stop Postgres mid-extract (errors, half-published extract?). | Experiment | Not started
P4-M9-05 | M9 Resilience | Failure-based exclusion with a deterministically failing task. | Experiment | Not started
P4-M9-06 | M9 Resilience | Bring services back; confirm workers re-register and the next run succeeds. | Task | Not started
P4-M9-07 | M9 Resilience | Each failure has a recorded timeline and a runbook entry. | Exit check | Not started
M10 Shuffle internals
P4-M10-01 | M10 Shuffle internals | Shuffle buffer and in-flight fetch settings on a large shuffle. | Experiment | Not started
P4-M10-02 | M10 Shuffle internals | Point the local directory somewhere specific and inspect shuffle files on a worker during a job. | Task | Not started
P4-M10-03 | M10 Shuffle internals | Relate shuffle write/read, spill and disk bytes in the Stages tab to the files. | Task | Not started
P4-M10-04 | M10 Shuffle internals | Check what happens when local disk fills. | Task | Not started
P4-M10-05 | M10 Shuffle internals | Each shuffle metric explained in terms of files and memory. | Exit check | Not started
M11 Capacity model
P4-M11-01 | M11 Capacity model | Write the capacity model: best layout, memory, storage settings and parallelism per workload class; where the bottleneck is; Postgres and RustFS limits; what changes when data doubles. Link experiment ids. | Task | Not started
P4-M11-02 | M11 Capacity model | Every workload has a named bottleneck with evidence; safe Postgres limits and storage settings recommended; failure runbook written. | Exit check | Not started

## P5_Streaming
Project 5: Streaming and CDC into Iceberg
Source: 05-streaming-cdc-lakehouse.md. Edit only the yellow cells: Status (dropdown), Started, Completed, Evidence / notes.
Progress | 0% | 0 of 77 items done ¦ In progress: 0 ¦ Blocked: 0 ¦ Skipped: 0
ID | Milestone | Task | Type | Status | Started | Completed | Evidence / notes
M0 Sources, speeds, SLOs
P5-M0-01 | M0 Sources, speeds, SLOs | Clickstream producer around real baskets, with duplicates/replays, malformed lines, schema drift, out-of-order events and ~2% very late events. | Task | Not started
P5-M0-02 | M0 Sources, speeds, SLOs | Write files safely (temporary name then rename); decide the object naming convention. | Task | Not started
P5-M0-03 | M0 Sources, speeds, SLOs | Run the lifecycle replayer with an adjustable time-compression factor. | Task | Not started
P5-M0-04 | M0 Sources, speeds, SLOs | Verify the change log is ordered and complete. | Task | Not started
P5-M0-05 | M0 Sources, speeds, SLOs | Choose three speeds: low (below capacity), medium (near), high (above). | Task | Not started
P5-M0-06 | M0 Sources, speeds, SLOs | Define service levels before building: freshness, completeness, duplicates, late-data tolerance. | Task | Not started
P5-M0-07 | M0 Sources, speeds, SLOs | Prepare batch reference truth for windows, sessions and current state. | Task | Not started
P5-M0-08 | M0 Sources, speeds, SLOs | Producers run at three speeds; change log verified; service levels written down. | Exit check | Not started
M1 Clickstream to bronze
P5-M1-01 | M1 Clickstream to bronze | File stream with an explicit schema and a files-per-trigger cap; decide how to treat corrupt lines and the drifted field. | Task | Not started
P5-M1-02 | M1 Clickstream to bronze | Write to Iceberg bronze with the checkpoint stored in RustFS. | Task | Not started
P5-M1-03 | M1 Clickstream to bronze | Inspect the checkpoint folder (offsets, commits, sources, metadata) and write down what each represents. | Task | Not started
P5-M1-04 | M1 Clickstream to bronze | Triggers: fixed interval vs available-now vs once. | Experiment | Not started
P5-M1-05 | M1 Clickstream to bronze | Prove exactly-once: restart several times (also mid-batch); compare bronze count with a batch read of the same objects. | Task | Not started
P5-M1-06 | M1 Clickstream to bronze | Watch progress metrics: input rate, processing rate, batch id, duration breakdown. | Task | Not started
P5-M1-07 | M1 Clickstream to bronze | Listing cost as the landing prefix grows; cleanup options (off / archive / delete). | Experiment | Not started
P5-M1-08 | M1 Clickstream to bronze | Decide bronze partitioning (ingestion day, hour, none) and predict file counts. | Task | Not started
P5-M1-09 | M1 Clickstream to bronze | Restarts never lose or duplicate; batch metrics understood; counts match batch reads. | Exit check | Not started
M2 Small files and maintenance
P5-M2-01 | M2 Small files and maintenance | After an hour at medium speed count data files and snapshots in bronze. | Task | Not started
P5-M2-02 | M2 Small files and maintenance | Run compaction and snapshot expiry while the stream runs; record conflicts and retries. | Experiment | Not started
P5-M2-03 | M2 Small files and maintenance | Sink options: fanout vs sorted write; target file size; distribution mode. | Experiment | Not started
P5-M2-04 | M2 Small files and maintenance | Find the trigger interval that meets both freshness and file-count targets. | Task | Not started
P5-M2-05 | M2 Small files and maintenance | Design the maintenance schedule (cadence, order, safe windows, margins relative to the checkpoint). | Task | Not started
P5-M2-06 | M2 Small files and maintenance | Schedule runs while the stream is live with a recorded conflict count; bronze stays within file-count targets. | Exit check | Not started
M3 Windowed aggregates
P5-M3-01 | M3 Windowed aggregates | One-minute tumbling and five-minute sliding counts by event type with a ten-minute watermark. | Task | Not started
P5-M3-02 | M3 Windowed aggregates | Find which output modes the Iceberg sink supports; route upserts through a batch-by-batch merge. | Task | Not started
P5-M3-03 | M3 Windowed aggregates | Watermark 1 min / 10 min / 1 h: emission delay, dropped rows, state size. | Experiment | Not started
P5-M3-04 | M3 Windowed aggregates | Reconcile dropped rows with the producer's known late events. | Task | Not started
P5-M3-05 | M3 Windowed aggregates | Tumbling vs sliding state size. | Experiment | Not started
P5-M3-06 | M3 Windowed aggregates | Compare the stream result with batch truth. | Task | Not started
P5-M3-07 | M3 Windowed aggregates | Stream matches batch except rows beyond the watermark, and you can explain the difference exactly. | Exit check | Not started
M4 Sessionization
P5-M4-01 | M4 Sessionization | 30-minute-gap sessions per user into gold: events, cart adds, conversions, revenue, start, end. | Task | Not started
P5-M4-02 | M4 Sessionization | Verify against a batch computation over the same period. | Task | Not started
P5-M4-03 | M4 Sessionization | Watermark lengths vs state size and memory per batch. | Experiment | Not started
P5-M4-04 | M4 Sessionization | Find the hot user's state partition in the metrics (the bulk buyer). | Task | Not started
P5-M4-05 | M4 Sessionization | Session gap 10 / 30 / 60 minutes. | Experiment | Not started
P5-M4-06 | M4 Sessionization | Stretch: arbitrary-state API (check PySpark availability); compare flexibility, cost, correctness. | Task | Not started
P5-M4-07 | M4 Sessionization | Streamed sessions equal batch sessions on closed periods; state growth model understood. | Exit check | Not started
M5 CDC apply
P5-M5-01 | M5 CDC apply | Poll the change log in micro-batches using the last applied sequence as the position. | Task | Not started
P5-M5-02 | M5 CDC apply | Collapse each batch to the latest change per key by sequence; separate inserts, updates, soft and hard deletes. | Task | Not started
P5-M5-03 | M5 CDC apply | MERGE into silver with match key, sequence comparison (ignore older changes) and delete handling. | Task | Not started
P5-M5-04 | M5 CDC apply | Make each batch idempotent; store the last applied batch or sequence atomically with the merge. | Task | Not started
P5-M5-05 | M5 CDC apply | Disorder tests: shuffle changes within a batch, replay old batches, drop one batch and detect the gap. | Experiment | Not started
P5-M5-06 | M5 CDC apply | Deletes: erasure requests (hard delete + anonymize) and cascade effects. | Experiment | Not started
P5-M5-07 | M5 CDC apply | Apply with MERGE vs append-only changelog + latest-per-key view (cost, audit, storage). | Experiment | Not started
P5-M5-08 | M5 CDC apply | Batch size small vs large (commit rate, conflict risk). | Experiment | Not started
P5-M5-09 | M5 CDC apply | Copy-on-write vs merge-on-read for the CDC target. | Experiment | Not started
P5-M5-10 | M5 CDC apply | Try incremental reads from an Iceberg table (streaming source, changelog view); document supported snapshot types. | Task | Not started
P5-M5-11 | M5 CDC apply | Replaying, reordering and dropping batches never corrupts silver; final state equals the batch rebuild. | Exit check | Not started
M6 Dedup and joins
P5-M6-01 | M6 Dedup and joins | Dedup by event id: classic with watermark vs within-watermark (state size, replays). | Experiment | Not started
P5-M6-02 | M6 Dedup and joins | Stream-static join against an updating silver dimension; prove whether updates become visible while the stream runs. | Task | Not started
P5-M6-03 | M6 Dedup and joins | Stream-stream join: views -> cart adds -> purchases with watermarks on both sides and a time-range condition. | Task | Not started
P5-M6-04 | M6 Dedup and joins | Outer join: when unmatched rows are emitted. | Experiment | Not started
P5-M6-05 | M6 Dedup and joins | Break it: remove a watermark; observe the error or unbounded state. | Task | Not started
P5-M6-06 | M6 Dedup and joins | Compare results with batch truth. | Task | Not started
P5-M6-07 | M6 Dedup and joins | Each pattern has documented state size, latency and correctness. | Exit check | Not started
M7 State and throughput tuning
P5-M7-01 | M7 State and throughput tuning | Change shuffle partitions on an existing stateful checkpoint; record what happens and why. | Task | Not started
P5-M7-02 | M7 State and throughput tuning | Default state store vs RocksDB for large state (memory, batch time, checkpoint size). | Experiment | Not started
P5-M7-03 | M7 State and throughput tuning | Raise producer rate until processing falls behind; control backlog with files-per-trigger and trigger interval. | Experiment | Not started
P5-M7-04 | M7 State and throughput tuning | Chart batch duration vs trigger interval from recent progress records. | Task | Not started
P5-M7-05 | M7 State and throughput tuning | Find the maximum sustainable rate and the first bottleneck (CPU, RustFS, commits, state). | Task | Not started
P5-M7-06 | M7 State and throughput tuning | Maximum sustainable rate per query and its first bottleneck known. | Exit check | Not started
M8 Failure drills
P5-M8-01 | M8 Failure drills | Kill a worker (executor loss, retries, no data loss). | Experiment | Not started
P5-M8-02 | M8 Failure drills | Stop the notebook kernel / kill the driver (restart from checkpoint, exact resume). | Experiment | Not started
P5-M8-03 | M8 Failure drills | Stop RustFS during a batch (error, retry, checkpoint and table state). | Experiment | Not started
P5-M8-04 | M8 Failure drills | Stop Postgres during CDC polling (resume without gaps or duplicates). | Experiment | Not started
P5-M8-05 | M8 Failure drills | Add a column to the sink table while running. | Experiment | Not started
P5-M8-06 | M8 Failure drills | Change the aggregation key or output mode (which errors?). | Experiment | Not started
P5-M8-07 | M8 Failure drills | Damage part of the checkpoint (what recovery is possible?). | Experiment | Not started
P5-M8-08 | M8 Failure drills | Each drill outcome matches prediction or the surprise is documented. | Exit check | Not started
M9 Latency and SLOs
P5-M9-01 | M9 Latency and SLOs | Mark a test change in Postgres; track it in the change log, micro-batch, silver and gold. | Task | Not started
P5-M9-02 | M9 Latency and SLOs | Break total latency into stages (poll, batch wait, processing, commit, visibility). | Task | Not started
P5-M9-03 | M9 Latency and SLOs | Latency at low, medium and high rates. | Experiment | Not started
P5-M9-04 | M9 Latency and SLOs | Write checks for each service level (freshness lag, counts vs batch truth, duplicates); confirm they fire when you break something. | Task | Not started
P5-M9-05 | M9 Latency and SLOs | Decide alert thresholds. | Task | Not started
P5-M9-06 | M9 Latency and SLOs | Freshness measured per stage; checks alert correctly. | Exit check | Not started
M10 Synthesis
P5-M10-01 | M10 Synthesis | Write the operating guide: topology, rates and limits, maintenance schedule, recovery steps, service levels and checks, monitoring. Link experiment ids. | Task | Not started
P5-M10-02 | M10 Synthesis | Silver and gold from the stream equal the batch rebuild on closed periods; failures never corrupt data; freshness measured with working checks. | Exit check | Not started

## Environment
Environment and versions
Record what you actually pinned. Do NOT store passwords or keys in this file.
Item | Suggested (from the guide) | Chosen / pinned | Date pinned | Verified how | Notes
Spark version | 4.x (see Gate A)
Scala version | 2.13
Java version | 17 or 21 (confirm in Spark docs)
Hadoop version bundled with Spark | from your Spark distribution
Iceberg Spark runtime artifact and version | must match Spark minor version
S3 access bundle (hadoop-aws + AWS SDK, or Iceberg AWS bundle) | versions must match Hadoop
PostgreSQL version
PostgreSQL JDBC driver version
RustFS release tag | pin a tag, not latest
Catalog type | JDBC on Postgres (recommended)
Source database name
Catalog database name | separate from source
Spark executor layout | 4 x (2 cores, 1 GB) to start
Default shuffle partitions chosen | 16 to 32 for 8 cores (data dependent)
Port: Spark master / master UI | 7077 / 8080
Port: application UI / history server | 4040 / 18080
Port: RustFS S3 API / console | 9000 / 9001
Port: PostgreSQL / Jupyter | 5432 / 8888
Where credentials are stored (do NOT write them here) | e.g. a password manager or env file
Dataset tiers built
Tier | Orders | Order lines | Lines per order | Built on | Random seed | Notes
Example (M, full data) | 3421083 | 33819106 | 9.8855 | 2026-11-02 | 42 | EXAMPLE - overwrite with your own build
S | [5 empty] | ~10% of users, all of their orders (about 340k orders, 3.4M lines)
M | [5 empty] | full dataset (3.42M orders, about 33.8M lines)
L | [5 empty] | full dataset replicated ~3 times (about 10M orders, 100M lines)

## Experiments
Experiment log
One row per experiment. Write the prediction BEFORE you run it. Row 6 is an example; overwrite or delete it.
Exp ID | Date | Project | Milestone | Prediction (before running) | Setting changed | Baseline | Result (time / bytes / shuffle / spill) | Spark UI evidence | Iceberg / RustFS / Postgres evidence | Conclusion | Follow-up | Prediction correct?
E-EX | 2026-11-02 | P2 | M5 Skew-fix ladder | AQE skew join will cut the max task time by half on the product-id join | skewJoin thresholds lowered to 32 MB | max/median task ratio 14x, 212 s | ratio 3x, 96 s, shuffle read 18 GB | Stage 7 task table; SQL plan shows skew=true | RustFS GET count unchanged; Postgres idle | AQE helps the join; no effect on the skewed aggregation | Try salting on the aggregation | Partly

## Defects
Defect register
Pre-filled with the Instacart issues to verify. Change Status to Confirmed / Handled / Not found as you profile. Row 6 is an example.
ID | Table | Column(s) | Description | Rows affected | Table rows | % of rows | Severity | How detected | Handling rule | Layer handled | Proving test | Status
D-EX | orders | days_since_prior_order | Null for each user's first order | 206209 | 3421083 | 6.028% | Low | Null rate by order_number | Keep null; derive is_first_order | Silver | Assert nulls only where order_number = 1 | Handled
D-001 | orders | eval_set | Test-set orders have no order lines at all |  |  |  | Medium | Anti-join of orders to both lines files | Keep in orders, flag has_lines = false, exclude from basket metrics | Silver |  | To verify
D-002 | order_products | order_id | Lines are split across two files (prior and train) that must be unioned |  |  |  | Medium | File inventory and row counts per file | Union with a source-file column | Bronze |  | To verify
D-003 | orders | days_since_prior_order | Null for each user's first order |  |  |  | Low | Null rate by order_number | Keep null; derive is_first_order | Silver |  | To verify
D-004 | orders | days_since_prior_order | Values appear capped near 30 days (censored data) |  |  |  | Medium | Value histogram spike at the cap | Treat the cap as 'at least 30'; document in cadence mart | Gold |  | To verify
D-005 | orders | order_dow, order_hour_of_day | No timestamps: only weekday, hour and gap since previous order |  |  |  | High | Schema review | Rebuilt timeline with quality flag | Source |  | To verify
D-006 | products | aisle_id, department_id | Placeholder 'missing' aisle and department |  |  |  | Medium | Distinct taxonomy values | Map to explicit 'unknown' | Silver |  | To verify
D-007 | products | product_name | Names contain commas and quotes that break naive CSV parsing |  |  |  | Low | Compare naive vs quoted-CSV row counts | Use a quoted-CSV reader | Landing |  | To verify
D-008 | order_products | order_id | Long tail of very large baskets |  |  |  | Low | Basket-size distribution | Cap or prune in co-occurrence work | Gold |  | To verify
D-009 | order_products | reordered | Possible disagreements between the reordered flag and user history |  |  |  | Medium | Rebuild flag from history and compare | Quarantine or flag disagreements | Silver |  | To verify
D-010 | orders | order_number | User histories may not line up with order_number (gaps or duplicates) |  |  |  | Medium | Contiguity check per user | Quarantine impossible histories | Silver |  | To verify
D-011 | (all) | price, payment, store, user | No prices, payments, stores or user attributes exist in the source |  |  |  | High | Schema review | Generate synthetic tables with documented rules | Source |  | To verify

## Decisions
Decision log
Decisions you must make during the lab. Fill in Evidence (experiment IDs), Choice and Status. Row 6 is an example.
ID | Date | Decision needed | Options considered | Evidence (experiment IDs) | Choice | Revisit if | Status
DEC-EX | 2026-11-02 | Bronze partitioning for lines | month of order date / bucket on order id / unpartitioned sorted | E-021, E-022 | month of order date | date filters stop dominating queries | Decided
DEC-001 |  | Spark version vs Iceberg runtime (Gate A) | Spark 4.2 if the runtime exists; else newest 4.x with a published Iceberg runtime |  |  |  | Open
DEC-002 |  | Catalog (Gate D) | Hadoop / JDBC on Postgres / standalone REST / RustFS built-in S3 Tables (preview) |  |  |  | Open
DEC-003 |  | Jar delivery (Gate C) | Baked into the image vs resolved at runtime |  |  |  | Open
DEC-004 |  | S3 access path | Hadoop S3A + AWS SDK bundle vs Iceberg's own S3 file I/O |  |  |  | Open
DEC-005 |  | S tier sampling method | By user (recommended) vs by order |  |  |  | Open
DEC-006 |  | Postgres lines table design | Single table vs partitioned by order date |  |  |  | Open
DEC-007 |  | Handling of test-set orders | Keep / flag / separate table |  |  |  | Open
DEC-008 |  | JDBC partitioning for order_items | Order-id ranges / hash / month / surrogate key |  |  |  | Open
DEC-009 |  | Snapshot consistency for the full extract | Shared repeatable-read snapshot / quiet window / accept and reconcile |  |  |  | Open
DEC-010 |  | Incremental strategy per table | Watermark / monotonic key / change-log polling / snapshot diff |  |  |  | Open
DEC-011 |  | Bronze typing | Typed vs all-string |  |  |  | Open
DEC-012 |  | Bronze partitioning for lines | Month / day of load / bucket on order id / department / unpartitioned sorted |  |  |  | Open
DEC-013 |  | Silver merge mode default | Copy-on-write vs merge-on-read |  |  |  | Open
DEC-014 |  | Maintenance cadence and snapshot retention | Per table type; balance time travel needs vs storage |  |  |  | Open

## Config_Cards
Configuration cards
One card per key setting. Defaults come from the configuration map; verify them in the Environment tab of the Spark UI. Fill the yellow cells after an experiment.
Project | Config | Default (verify) | What it controls | Too low / too high | How I observed it | Value chosen and why | Interacts with | Learned?
P1/P2 | spark.sql.shuffle.partitions | 200 | Partitions after a shuffle (joins, aggregates) |  |  |  |  | Not started
P2/P3 | spark.sql.adaptive.enabled | true | AQE master switch |  |  |  |  | Not started
P2 | spark.sql.adaptive.advisoryPartitionSizeInBytes | 64MB | Target partition size after coalescing or skew split |  |  |  |  | Not started
P2 | spark.sql.adaptive.skewJoin.enabled | true | Splits skewed partitions in sort-merge joins |  |  |  |  | Not started
P2 | spark.sql.autoBroadcastJoinThreshold | 10MB | Auto-broadcast size limit (-1 disables) |  |  |  |  | Not started
P4 | spark.executor.cores | all worker cores (standalone) | Cores per executor |  |  |  |  | Not started
P4 | spark.executor.memory | 1g | Executor heap |  |  |  |  | Not started
P4 | spark.cores.max | unlimited | Total cores an application may take |  |  |  |  | Not started
P2 | spark.driver.memory | 1g | Driver heap (collect, broadcast build) |  |  |  |  | Not started
P4 | spark.memory.fraction | 0.6 | Heap share for execution plus storage |  |  |  |  | Not started
P4 | spark.memory.storageFraction | 0.5 | Part of that share protected for cache |  |  |  |  | Not started
P1 | JDBC numPartitions | unset | Read/write parallelism and max concurrent connections |  |  |  |  | Not started
P1 | JDBC partitionColumn / lowerBound / upperBound | unset | Range split for parallel reads |  |  |  |  | Not started
P1 | JDBC fetchsize | driver default | Rows per round trip; executor memory |  |  |  |  | Not started
P1 | Iceberg write.target-file-size-bytes | 512MB | Target data file size |  |  |  |  | Not started
P2 | Iceberg write.distribution-mode | check | Shuffle before write: none, hash, range |  |  |  |  | Not started
P1 | Iceberg write.merge.mode (and update/delete) | copy-on-write | Copy-on-write vs merge-on-read |  |  |  |  | Not started
P4 | S3A fs.s3a.connection.maximum | check | Concurrent HTTP connections to RustFS |  |  |  |  | Not started
P4 | Iceberg read.split.target-size | 128MB | Scan task size for Iceberg tables |  |  |  |  | Not started
P4 | spark.sql.execution.arrow.pyspark.enabled | check | Arrow for pandas conversion |  |  |  |  | Not started
P4 | spark.dynamicAllocation.enabled (+ shuffleTracking) | false | Scale executors up and down; tracking needed in standalone |  |  |  |  | Not started
P4 | spark.speculation | false | Re-run slow tasks |  |  |  |  | Not started
P1 | spark.sql.ansi.enabled | true in 4.x | Strict casts and overflow errors; use try_* functions |  |  |  |  | Not started
P1 | spark.sql.sources.partitionOverwriteMode | static | dynamic overwrites only touched partitions |  |  |  |  | Not started
P3 | spark.sql.files.maxPartitionBytes | 128MB | Scan partition size for file sources (not Iceberg tables) |  |  |  |  | Not started
P3 | spark.sql.cbo.enabled | false | Use statistics for cost-based planning |  |  |  |  | Not started
P3 | spark.sql.optimizer.dynamicPartitionPruning.enabled | true | Prune partitions via joins |  |  |  |  | Not started
P3 | spark.sql.optimizer.runtime.bloomFilter.enabled | check | Bloom-filter runtime filter |  |  |  |  | Not started
P5 | Streaming checkpointLocation | none | Offsets, commits and state |  |  |  |  | Not started
P5 | Streaming trigger | as fast as possible | Fixed interval or available-now |  |  |  |  | Not started
P5 | spark.sql.streaming.stateStore.providerClass | HDFS-backed | RocksDB provider for large state |  |  |  |  | Not started
P5 | spark.sql.shuffle.partitions (stateful queries) | 200 | Fixed per checkpoint once the stream has state |  |  |  |  | Not started
All | spark.eventLog.enabled / spark.eventLog.dir | false | Event logs for the history server (can point at a bucket) |  |  |  |  | Not started